## Sheet1
1 | Travel Management Project | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date
1.1 | Employee Management | 15/10/2023 | 20/10/2023 | 15/10/2023 | 21/10/2023
1.1.1 | Add Employee | 15/10/2023 | 16/10/2023 | 15/10/2023 | 16/10/2023
1.1.2 | View Employee | 15/10/2023 | 16/10/2023 | 15/10/2023 | 16/10/2023
1.1.3 | Edit Employee | 16/10/2023 | 18/10/2023 | 16/10/2023 | 18/10/2023
1.1.4 | Delete Employee | 16/10/2023 | 19/10/2023 | 16/10/2023 | 18/10/2023
1.2 | Travel Management | 20/10/2023 | 29/10/2023 | 21/10/2023 | 30/10/2023
1.2.1 | Raise Travel Request | 21/10/2023 | 22/10/2023 | 21/10/2023 | 22/10/2023
1.2.2 | View Travel Request | 23/10/2023 | 23/10/2023 | 23/10/2023 | 23/10/2023
1.2.3 | Edit Travel Request | 23/10/2023 | 24/10/2023 | 23/10/2023 | 24/10/2023
1.2.4 | Delete Travel Request | 24/10/2023 | 25/10/2023 | 24/10/2023 | 25/10/2023
1.2.5 | Approve Travel Request | 24/10/2023 | 25/10/2023 | 24/10/2023 | 25/10/2023
1.2.6 | Confirm Travel Request | 25/10/2023 | 25/10/2023 | 25/10/2023 | 25/10/2023
1.2.7 | View All Travel Request | 26/10/2023 | 26/10/2023 | 26/10/2023 | 26/10/2023
1.2.8 | View All Approved Travel Request | 27/10/2023 | 27/10/2023 | 27/10/2023 | 27/10/2023
1.2.9 | View Travel Request by Month | 27/10/2023 | 27/10/2023 | 27/10/2023 | 27/10/2023
1.2.10 | View Travel Request by From Location | 28/10/2023 | 28/10/2023 | 28/10/2023 | 28/10/2023
1.2.11 | View Travel Request by To Location | 29/10/2023 | 29/10/2023 | 29/10/2023 | 29/10/2023
1.3 | Documentation/ Presentation | 2023-01-11 | 2023-01-11 | 2023-02-11 | 2023-02-11
1.4 | Correction / Feedback Enhancement | 2023-11-01 | 2023-11-05 | 2023-11-01 | 2023-11-05
1.4.1 | Employee Management Feedback
1.4.1.1 | No repetetion of Employee Id
1.4.1.2 | To select employee for delete/edit only form list
1.4.2 | Travel Request Management Feedback
1.4.2.1 | No repetetion of Employee Id
1.4.2.2 | To select employee for delete/edit only form list
1.4.2.3 | To approve requests only show pending requests
1.4.2.4 | To confirm requests only show approved requests
1.4.2.5 | If requests are approved and confirmed close request
1.4.2.6 | If requests are approved and not confirmed close request
1.4.2.7 | To not approve request close requests